## Project Management Sample Data_
End Date | Location | Overall Project Health | Priority | Project ID | Project Manager | Project Name | Project Type | Start Date | Status | % Complete | Budget | Expense | Latitude | Longitude
2019-10-25 | New York | On Track | Medium | 1 | Sophia Quinn | Auditorium Setup 1 | Facilities | 2019-05-30 | In Progress | 0.93 | 2000 | 0 | 43 | -75.49
2020-04-20 | North Dakota | On Track | Very Low | 2 | James Potter | Lab Implementation 1 | Facilities | 2019-07-30 | In Progress | 0.95 | 20000 | 19800 | 47.5 | -100
2020-02-03 | Idaho | On Track | Very High | 3 | James Potter | Park Place 1 | Network Services | 2019-08-19 | In Progress | 0.46 | 8700 | 6490 | 44.0739 | -114.542
2020-02-21 | Texas | On Track | Low | 4 | James Potter | Science Park Phase 2 | Performance Management | 2019-08-19 | In Progress | 0.59 | 10000 | 7540 | 31.25 | -99.25
2020-03-06 | Idaho | On Track | Low | 5 | James Potter | Research Offices | Performance Management | 2019-08-19 | In Progress | 0.22 | 7000 | 6500 | 44.0739 | -114.542
2020-04-01 | Kansas | On Track | Very High | 6 | James Potter | Innovation Classroom | Performance Management | 2019-08-27 | On Hold | 0.61 | 15000 | 8700 | 38.5 | -98.5
2020-04-20 | North Dakota | On Track | Very Low | 7 | James Potter | Lab Implementation | Client Service | 2019-07-30 | In Progress | 0.95 | 12000 | 13900 | 47.5 | -100
2020-02-03 | Idaho | On Track | Medium | 8 | James Potter | Park Place 2 | Security Services | 2019-08-19 | In Progress | 0.46 | 9080 | 2560 | 44.0739 | -114.542
2020-04-20 | North Dakota | On Track | High | 9 | James Potter | Lab Implementation | Security Services | 2019-07-30 | In Progress | 0.95 | 18000 | 11500 | 47.5 | -100
2020-02-03 | Idaho | On Track | High | 10 | James Potter | Park Place 3 | Research Support | 2019-08-19 | In Progress | 0.46 | 3400 | 2300 | 44.0739 | -114.542
2020-08-19 | Alabama | Needs Attention | Very Low | 11 | Sophia Quinn | Lab Facilities 1 | Facilities | 2020-08-15 | Planned | 0 | 63600 | 0 | 32.75 | -86.75
2020-03-06 | Idaho | On Track | Very Low | 12 | James Potter | Research Offices | Network Services | 2019-08-19 | In Progress | 0.22 | 6000 | 4080 | 44.0739 | -114.542
2020-03-06 | Idaho | On Track | Medium | 13 | James Potter | Research Offices | Performance Management | 2019-08-19 | In Progress | 0.22 | 4300 | 4450 | 44.0739 | -114.542
2020-03-06 | Idaho | On Track | Low | 14 | James Potter | Research Offices | Research Support | 2019-08-19 | In Progress | 0.22 | 5500 | 1000 | 44.0739 | -114.542
2019-10-25 | New York | On Track | Low | 15 | Sophia Quinn | Classroom Arrangement | Research Support | 2019-05-31 | In Progress | 0.93 | 34500 | 30000 | 43 | -75.49
2020-02-21 | Texas | On Track | Very Low | 16 | James Potter | Science Park 1 | Facilities | 2019-08-19 | In Progress | 0.59 | 7000 | 6580 | 31.25 | -99.25
2020-10-01 | Idaho | Needs Attention | Very High | 17 | James Potter | Creative Media Industries 1 | Facilities | 2020-08-31 | Planned | 0 | 4500 | 0 | 44.0739 | -114.542
2019-12-13 | North Dakota | On Track | Medium | 18 | Sean Thomas | Lab Implementation | Network Services | 2019-09-13 | In Progress | 0.35 | 23000 | 20340 | 47.5 | -100
2019-07-26 | Arizona | Not Set | Very High | 19 | Sophia Quinn | Central Deployment | Performance Management | 2019-06-21 | On Hold | 0.14 | 1500 | 980 | 34.5 | -111.5
2020-02-21 | Texas | On Track | Very Low | 20 | James Potter | Science Park 2 | Facilities | 2019-08-19 | In Progress | 0.59 | 9800 | 9050 | 31.25 | -99.25
2020-10-15 | Alabama | Needs Attention | Very High | 21 | Sophia Quinn | Lab Facilities 2 | Facilities | 2020-09-15 | Planned | 0 | 23000 | 0 | 32.75 | -86.75
2020-10-18 | Idaho | Needs Attention | Very High | 22 | James Potter | Creative Media Industries 2 | Facilities | 2020-10-01 | Planned | 0 | 1200 | 0 | 44.0739 | -114.542
2019-12-13 | North Dakota | On Track | Medium | 23 | Sean Thomas | Classroom Arrangement 1 | Facilities | 2019-09-13 | In Progress | 0.35 | 12300 | 15000 | 47.5 | -100
2020-11-28 | Alabama | Not Set | Very Low | 24 | Sophia Quinn | Classroom Arrangement | Network Services | 2020-11-04 | Planned | 0 | 2340 | 0 | 32.75 | -86.75
2020-10-26 | Alabama | Not Set | Medium | 25 | Sophia Quinn | Classroom Arrangement | Performance Management | 2020-09-06 | Planned | 0 | 1500 | 0 | 32.75 | -86.75
2021-01-05 | Alabama | Needs Attention | Low | 26 | Sophia Quinn | Lab Facilities 3 | Facilities | 2020-12-15 | Planned | 0 | 750 | 0 | 32.75 | -86.75
2020-09-30 | Idaho | Needs Attention | Low | 27 | James Potter | Creative Media Industries | Security Services | 2020-09-24 | Planned | 0 | 45000 | 0 | 44.0739 | -114.542
2020-09-30 | North Dakota | On Track | Medium | 28 | Sean Thomas | Classroom Arrangement 2 | Facilities | 2020-09-24 | Planned | 0 | 1230 | 0 | 47.5 | -100
2020-05-08 | North Dakota | On Track | Very Low | 29 | Cam John | Innovation Classroom | Security Services | 2019-11-25 | In Progress | 0.76 | 53855 | 42560 | 47.5 | -100
2020-02-21 | Texas | On Track | Low | 30 | James Potter | Science Park 3 | Facilities | 2019-08-19 | In Progress | 0.59 | 3500 | 3560 | 31.25 | -99.25
2020-08-29 | Idaho | Needs Attention | Medium | 31 | James Potter | Creative Media Industries | Security Services | 2020-08-20 | Planned | 0 | 790 | 0 | 44.0739 | -114.542
2019-12-13 | North Dakota | On Track | High | 32 | Sean Thomas | Classroom Arrangement 3 | Facilities | 2019-09-13 | In Progress | 0.35 | 10000 | 4500 | 47.5 | -100
2019-07-26 | Arizona | Not Set | High | 33 | Sophia Quinn | Central Deployment | Security Services | 2019-06-21 | On Hold | 0.14 | 2000 | 3400 | 34.5 | -111.5
2020-02-21 | Texas | On Track | Low | 34 | James Potter | Science Park 4 | Facilities | 2019-08-19 | In Progress | 0.59 | 4000 | 3700 | 31.25 | -99.25
2019-10-25 | New York | On Track | Very High | 35 | Sophia Quinn | Classroom Arrangement | Security Services | 2019-05-31 | In Progress | 0.93 | 7000 | 5690 | 43 | -75.49
2020-12-01 | Texas | On Track | High | 36 | James Potter | Central Deployment | Network Services | 2020-03-10 | In Progress | 0.39 | 36000 | 25350 | 31.25 | -99.25
2019-11-20 | Alabama | On Track | High | 37 | James Potter | External Wi-Fi Expansion | Performance Management | 2019-05-25 | In Progress | 0.89 | 3400 | 3100 | 32.75 | -86.75
2019-11-14 | Texas | On Track | Very High | 38 | James Potter | Ticketing System | Client Service | 2019-06-16 | In Progress | 0.6 | 4560 | 6510 | 31.25 | -99.25
2019-10-25 | New York | On Track | Low | 39 | Sophia Quinn | Auditorium Setup 2 | Facilities | 2019-05-31 | In Progress | 0.93 | 9585 | 9500 | 43 | -75.49
2019-10-25 | New York | On Track | Low | 40 | Sophia Quinn | Auditorium Setup 3 | Facilities | 2019-05-31 | In Progress | 0.93 | 6000 | 0 | 43 | -75.49
2019-12-17 | Idaho | On Track | Very High | 41 | Lucy Tipton | External Wi-Fi Expansion | Security Services | 2019-07-06 | On Hold | 0.5 | 1200 | 500 | 44.0739 | -114.542
2019-11-14 | Texas | On Track | Low | 42 | James Potter | Ticketing System | Security Services | 2019-06-16 | In Progress | 0.6 | 23000 | 21000 | 31.25 | -99.25
2019-10-25 | New York | On Track | Medium | 43 | Sophia Quinn | Auditorium Setup 4 | Facilities | 2019-05-31 | In Progress | 0.93 | 4000 | 0 | 43 | -75.49
2020-12-31 | Idaho | Not Set | Very Low | 44 | James Potter | Park Place 4 | Security Services | 2020-12-17 | Planned | 0 | 7000 | 0 | 44.0739 | -114.542
2019-12-28 | Alabama | Needs Attention | Very High | 45 | Jim Jones | Innovation Classroom | Security Services | 2019-07-22 | Completed | 1 | 16000 | 14560 | 32.75 | -86.75
2020-03-25 | Idaho | Needs Attention | Medium | 46 | James Potter | Floor Renovation 1 | Facilities | 2019-07-17 | Completed | 1 | 4565 | 2365 | 44.0739 | -114.542
2019-12-28 | Alabama | Needs Attention | Medium | 47 | Jim Jones | Education Theatre 1 | Facilities | 2019-07-22 | Completed | 1 | 3400 | 1240 | 32.75 | -86.75
2019-11-22 | Texas | On Track | Medium | 48 | Lucy Tipton | Sculpture Building | Security Services | 2019-07-26 | In Progress | 0.36 | 2300 | 1760 | 31.25 | -99.25
2020-02-21 | Texas | On Track | Medium | 49 | James Potter | Science Park 5 | Facilities | 2019-08-19 | In Progress | 0.59 | 1235 | 760 | 31.25 | -99.25
2020-02-25 | Idaho | Needs Attention | High | 50 | James Potter | Creative Media Industries 3 | Facilities | 2019-08-09 | Completed | 1 | 1500 | 1235 | 44.0739 | -114.542
2019-12-13 | North Dakota | On Track | Low | 51 | Sean Thomas | Classroom Arrangement 4 | Facilities | 2019-09-13 | In Progress | 0.35 | 15000 | 4355 | 47.5 | -100
2019-10-25 | New York | On Track | Very High | 52 | Sophia Quinn | Classroom Arrangement | Security Services | 2019-05-31 | In Progress | 0.93 | 500 | 600 | 43 | -75.49
2020-02-21 | Texas | On Track | High | 53 | James Potter | Science Park 6 | Facilities | 2019-08-19 | In Progress | 0.59 | 1455 | 970 | 31.25 | -99.25
2020-03-06 | Idaho | On Track | Very High | 54 | James Potter | Research Offices 1 | Facilities | 2019-08-19 | In Progress | 0.22 | 6000 | 5890 | 44.0739 | -114.542
2020-04-01 | Kansas | On Track | Very Low | 55 | James Potter | Innovation Classroom | Security Services | 2019-08-27 | On Hold | 0.61 | 1235 | 760 | 38.5 | -98.5
2020-04-20 | North Dakota | On Track | Medium | 56 | James Potter | Lab Implementation 2 | Facilities | 2019-07-30 | In Progress | 0.95 | 1500 | 1235 | 47.5 | -100
2020-03-25 | Idaho | Needs Attention | Low | 57 | James Potter | Park Place 5 | Security Services | 2019-07-17 | Completed | 1 | 3400 | 3100 | 44.0739 | -114.542
2019-12-28 | Alabama | Not Set | Very Low | 58 | Jim Jones | Education Theatre 2 | Facilities | 2019-07-22 | Completed | 1 | 2400 | 1000 | 32.75 | -86.75
2020-03-25 | Idaho | Needs Attention | Very Low | 59 | James Potter | Park Place 6 | Network Services | 2019-07-17 | Completed | 1 | 9585 | 9500 | 44.0739 | -114.542
2019-12-28 | Alabama | Needs Attention | Very Low | 60 | Jim Jones | Innovation Classroom | Performance Management | 2019-07-22 | Completed | 1 | 10000 | 8600 | 32.75 | -86.75
2020-03-25 | Idaho | Needs Attention | Very Low | 61 | James Potter | Floor Renovation 2 | Facilities | 2019-07-17 | Completed | 1 | 8000 | 6400 | 44.0739 | -114.542
2019-11-20 | North Dakota | On Track | Medium | 62 | Cam John | Innovation Classroom | Client Service | 2019-10-19 | In Progress | 0.49 | 51345 | 47680 | 47.5 | -100
2020-02-21 | Texas | On Track | High | 63 | James Potter | Science Park 7 | Facilities | 2019-08-19 | In Progress | 0.59 | 4300 | 0 | 31.25 | -99.25
2020-03-06 | Idaho | On Track | Low | 64 | James Potter | Research Offices 2 | Facilities | 2019-08-19 | In Progress | 0.22 | 1200 | 250 | 44.0739 | -114.542
2020-04-01 | Kansas | On Track | Very Low | 65 | James Potter | Network Connectivity | Facilities | 2019-08-27 | On Hold | 0.61 | 1340 | 540 | 38.5 | -98.5
2020-04-20 | North Dakota | On Track | Very Low | 66 | James Potter | Lab Implementation | Security Services | 2019-07-30 | Cancelled | 0.95 | 2340 | 2600 | 47.5 | -100
2020-08-25 | Idaho | Needs Attention | Very High | 67 | James Potter | Park Place 7 | Client Service | 2019-08-17 | Planned | 0 | 930 | 0 | 44.0739 | -114.542
2019-12-28 | Alabama | Not Set | Very Low | 68 | Jim Jones | Education Theatre 3 | Facilities | 2019-07-22 | Completed | 1 | 6000 | 4300 | 32.75 | -86.75
2020-03-25 | Idaho | Needs Attention | Low | 69 | James Potter | Floor Renovation 3 | Facilities | 2019-07-17 | Completed | 1 | 2400 | 1000 | 44.0739 | -114.542
2019-12-28 | Alabama | Needs Attention | Medium | 70 | Jim Jones | Education Theatre 4 | Facilities | 2019-07-22 | Completed | 1 | 16000 | 10090 | 32.75 | -86.75
2020-02-21 | Texas | On Track | Medium | 71 | James Potter | Ticketing System | Network Services | 2019-08-19 | Cancelled | 0.59 | 3400 | 0 | 31.25 | -99.25
2020-02-25 | Idaho | Not Set | Very High | 72 | James Potter | Park Place 8 | Performance Management | 2019-08-09 | Completed | 1 | 23000 | 10590 | 44.0739 | -114.542
2019-12-13 | North Dakota | On Track | High | 73 | Sean Thomas | Classroom Arrangement 5 | Facilities | 2019-09-13 | Cancelled | 0.35 | 15000 | 5550 | 47.5 | -100
2019-07-26 | Arizona | Not Set | Medium | 74 | Sophia Quinn | Training Room | Facilities | 2019-06-21 | On Hold | 0.14 | 16000 | 16890 | 34.5 | -111.5
2020-02-21 | Texas | On Track | Low | 75 | James Potter | Ticketing System | Network Services | 2019-08-19 | Cancelled | 0.59 | 3400 | 2300 | 31.25 | -99.25
2019-10-28 | Alabama | Needs Attention | Very Low | 76 | Sophia Quinn | Classroom Arrangement | Performance Management | 2019-09-23 | Completed | 1 | 23000 | 21450 | 32.75 | -86.75
2020-02-25 | Idaho | Needs Attention | Very Low | 77 | James Potter | Creative Media Industries 4 | Facilities | 2019-08-09 | Completed | 1 | 1500 | 1340 | 44.0739 | -114.542
2019-12-13 | North Dakota | On Track | Medium | 78 | Sean Thomas | Classroom Arrangement 6 | Facilities | 2019-09-13 | Cancelled | 0.35 | 16000 | 15465 | 47.5 | -100
2019-10-28 | Alabama | Needs Attention | Low | 79 | Sophia Quinn | Classroom Arrangement | Performance Management | 2019-09-23 | Completed | 1 | 13400 | 7000 | 32.75 | -86.75
2019-10-28 | Alabama | Not Set | Very High | 80 | Sophia Quinn | Classroom Arrangement | Client Service | 2019-09-23 | Completed | 1 | 23000 | 20345 | 32.75 | -86.75
2019-10-28 | Alabama | Needs Attention | High | 81 | Sophia Quinn | Classroom Arrangement | Network Services | 2019-09-23 | Completed | 1 | 10500 | 10240 | 32.75 | -86.75
2020-02-25 | Idaho | Needs Attention | Low | 82 | James Potter | Park Place 9 | Performance Management | 2019-08-09 | Completed | 1 | 5000 | 3400 | 44.0739 | -114.542
2020-12-13 | North Dakota | On Track | High | 83 | Sean Thomas | Classroom Arrangement 7 | Facilities | 2020-09-13 | Planned | 0 | 1000 | 0 | 47.5 | -100